## Overview
Field | Value
Program | Dear Jobs Engineering
Welcome | Welcome, new SDET.
Context | You joined a 10-person product team maintaining an existing job-search platform.
Learning goal | Complete real sprint work: explore APIs in Postman, investigate unclear requirements, automate with Playwright, and respond to code review.
Sprint | Sprint 01
Day | Day 4 of 10
Sprint goal | Find, filter & save jobs
Progress | 38% complete
Story points delivered | 4

## Assigned Work
Ticket | Title | Details | Status
DJ-106 | Create Postman tests for Jobs API | Positive, negative, schema, JWT, chained requests and Newman execution. | In progress
DJ-109 | Explore combined job filters | Assigned by Tech Lead; 60-minute charter; QA environment. | Ready
DJ-107 | Automate job-search smoke flow | Playwright + TypeScript; starts after DJ-106 review. | Blocked

## Test Charter
Field | Value
Tech Lead | Maya Chen
Charter | Explore combinations of location, Remote, C2C, and H-1B Transfer filters.
Focus | Invalid values; navigation persistence; empty results; UI/API inconsistencies.
Deliverables | Capture evidence and identify automation candidates.

## Definition of Ready
Item | State
Business value is clear | Ready
Acceptance criteria are testable | Ready
API contract is missing | Gap
Remote vs hybrid rule unresolved | Gap
Test data is identified | Ready
Performance threshold unspecified | Gap

## Ceremonies
Time | Ceremony | Purpose
09:15 | Daily stand-up | Report progress, plan, blockers.
14:00 | PR review | Senior SDET + Tech Lead.